## Risk Register
Risk_ID | Risk | Probability | Impact | Owner | Mitigation | Status
R-001 | Small EC2 instance runs out of memory during dependency install | 0.45 | Medium | Deployment | Add 2 GB swap and keep dependencies lean | Mitigated
R-002 | Nginx route returns 404 for /api/health | 0.35 | Medium | Deployment | Link agentic-crag site, remove default site, validate nginx -t, reload nginx | Mitigated
R-003 | Wrong public IP in SSH security group | 0.4 | High | Deployment | Update inbound SSH source to current public IPv4 /32 | Mitigated
R-004 | Missing source citations reduce trust in RAG answers | 0.7 | High | RAG | Return source snippets and retrieval scores in chat responses | Mitigated
R-005 | Pure vector retrieval misses exact IDs or codes | 0.55 | Medium | RAG | Consider hybrid keyword plus vector search in future | Open
R-006 | Spreadsheet answers omit rows | 0.3 | High | RAG | Use larger spreadsheet chunks and test numeric questions | Monitoring
R-007 | User uploads confidential files to hybrid demo | 0.25 | High | Security | Warn that retrieved excerpts are sent to external LLM provider | Mitigated
R-008 | No authentication on public demo | 0.5 | High | Security | Use temporary demo only, add auth before long-lived sharing | Open

## Incident Log
Incident_ID | Date | Symptom | Root_Cause | Fix
I-001 | 2026-06-14 | SSH connection timed out | Security group allowed old public IP address | Updated SSH inbound source to current public IPv4 /32
I-002 | 2026-06-14 | SSH rejected PEM file | Windows key file permissions too open | Moved key to .ssh and restricted ACLs
I-003 | 2026-06-14 | pip failed on pywinpty | Old repository requirements included Windows-only dependency | Cleaned requirements and pushed deployment repo
I-004 | 2026-06-14 | curl /api/health returned Nginx 404 | Nginx default or inactive site config | Install/link agentic-crag Nginx config and reload service